## Sheet1
Work Breakdown Structure
Project Name: HealthFirst Care
Project Manager: Seth Haynes
Level 1 |  |  | 1.0 HealthFirst Care Improvement Initiative
Level 2 | 1.1 Requirements Gathering and Analysis | 1.2 Current Process Analysis and Workflow Improvement | 1.3 Appointment Scheduling and Patient Communication Improvements | 1.4 Resource, Records and Workflow Improvements | 1.5 Dashboard and Reporting Development | 1.6 Testing and Validation | 1.7 Implementation and Project Handover
Level 3 | 1.1.1 Conduct stakeholder interviews | 1.2.1 Document current appointment scheduling process | 1.3.1 Define automated scheduling requirements | 1.4.1 Define staff, room and equipment availability requirements | 1.5.1 Define dashboard information requirements | 1.6.1 Develop acceptance criteria | 1.7.1 Prepare implementation plan
| 1.1.2 Analyse appointment data | 1.2.2 Document current patient communication process | 1.3.2 Define real-time availability requirements | 1.4.2 Define resource status and tracking requirements | 1.5.2 Define appointment performance measures | 1.6.2 Validate scheduling functionality | 1.7.2 Prepare staff guidance and training
| 1.1.3 Analyse patient feedback data | 1.2.3 Document resource allocation and availability process | 1.3.3 Define duplicate-booking prevention rules | 1.4.3 Define standardised handoff and referral requirements | 1.5.3 Define patient satisfaction measures | 1.6.3 Validate patient notification functionality | 1.7.3 Communicate changes to affected stakeholders
| 1.1.4 Analyse resource allocation data | 1.2.4 Document handoff and referral processes | 1.3.4 Define online booking usability requirements | 1.4.4 Define patient record retrieval requirements | 1.5.4 Define resource utilisation measures | 1.6.4 Validate resource visibility | 1.7.4 Implement approved workflow and system improvements
| 1.1.5 Document and prioritise business requirements | 1.2.5 Identify process gaps and improvement opportunities | 1.3.5 Define SMS/email notification requirements | 1.4.5 Define scheduling, treatment and billing integration requirements | 1.5.5 Develop operational dashboards | 1.6.5 Validate handoff and record workflows | 1.7.5 Monitor initial operational performance
| 1.1.6 Milestone: BRD complete and approved | 1.2.6 Design proposed future-state workflows | 1.3.6 Define cancellation, rescheduling and delay notification rules | 1.4.6 Milestone: Operational improvement requirements approved | 1.5.6 Validate dashboard information with stakeholders | 1.6.6 Validate dashboards and reporting | 1.7.6 Compare results against project objectives
|  | 1.2.7 Milestone: Stakeholder sign-off on optimised workflows | 1.3.7 Milestone: Scheduling and notification solution requirements approved |  | 1.5.7 Milestone: Operational dashboards completed | 1.6.7 Record and resolve identified issues | 1.7.7 Milestone: HealthFirst Care improvements implemented
[6 empty] | 1.6.8 Milestone: Solution accepted by stakeholders | 1.7.8 Milestone: Project handover completed