## Stakeholder Matrix
Stakeholder Matrix
Project Title: HealthFirst Care Capstone Project
Project Manager: Seth Haynes
Stakeholder Name/Group | Role/Responsibility | Influence Level (High/Low) | Interest Level (High/Low) | Classification | Key Requirements | Engagement Strategy | Frequency of Interaction | Communication Method | Purpose of Engagement
Project Sponsors | Approve project decisions and resources. Oversee achievement of hospital objectives. | High | High | Key Players | Measurable imporvement in patient experience, operational efficiency, and resource allocation. | Project meetings. Progress reports/dashboards. | Weekly | Meetings. Reports/dashboards. | Review progress against objectives. Approval. Monitor risks.
Hospital Management | Provide strategic direction for hospital. Approve decisions and resources. Oversee achievement of hospital objectives | High | High | Key Players | Measurable imporvement in patient experience, operational efficiency, and resource allocation. | Project meetings. Progress reports/dashboards. | Weekly | Meetings. Reports/dashboards | Review progress against objectives. Resolve escalated issues. Approval. Monitor risks.
Doctors | Patient care. Use scheduling software, hospital resources, diagnostic information, and interdepartmental processes. | High | High | Key Players | Reliable schedules. Adequate rooms, equipment, and supplies.Faster diagnostic results. Imporved referrals and handoff communication. | Requirements gathering workshops. Project meetings. Interviews. | Weekly | Workshops. Meetings. Interviews. | Gather operational requirements. Proposed workflows. Ensure changes support safe and efficiet patient care.
Nurses | Patient care. Use scheduling software, hospital resources, diagnostic information, and interdepartmental processes. | Low | High | Keep Informed | Reliable schedules. Adequate staff and equipment. Improved referrals and handoff communication. | Requirements gathering workshops. Project meetings. | Weekly | Workshops. Meetings. | Gather operational requirements. Proposed workflows. Ensure changes support safe and efficiet patient care.
Administrative Staff | Manage appointment scheduling, patient records, billing information, and other administrative processes. | High | High | Key Players | Redcued double bookings. Real time doctor availability. Easier record retrival. Improved system alignment for scheduling, treatment, and billing information. | Requirements gathering workshops. Meetings. System demonstrations. User testing. | Weekly | Workshops. Meetings. Demonstrations. Testing. | Gather scheduling, records, and billing requirements. Test proposed processes and identify issues.
IT Teams | Maintain and develop hosiptal information systems. Support integration, security, and technical implementation. | High | Low | Keep Satisfied | Integrated systems. Reduced data silos. Improved security. Scalable appointment capability. Real time notifications and analytics. | Technical meetings. Email updates. Technical documentation. Progress reports | Bi-weekly | Meetings. Emails. Progress reports. Documentation, | Confirm technical feasibility. Identify system problems and security concerns. Ensure propsed requirements can be implemented.
Patiens | Receive care from hsopital. Interact with appointment, communication, and follow up processes. | Low | High | Keep Informed | User-friendly booking. Shorter wait times, Real time appointment notifications. Clear post-consultation follow-up support | Surveys. Newsletters. Key milestone email updates. | Monthly | Surveys. Email | Gather patient feedback. Validate usability. Measure satisfaction.
Support Staff | Non-clinical duties. Ensure facilities operate safely and efficiency. | Low | Low | Monitor | Adequate equipment. Good comminication of work in and between departments. | Meeting notes. General staff updates. Email reports. | As needed | Email | Maintain basic awareness of relevant project changes.