## Risk Register and Contingency
Risk Register | [7 empty] | 1-2 = Low
Project Name: Healthcare First Capstone Project | [7 empty] | 3-4 = Medium
Project Manager: Seth Haynes | [7 empty] | 6-9 = High
Risk ID | Risk Description | Category | Likelihood | Impact | Serverity | Mitigation Strategy | Conteingency Plan
R-01 | Appointment scheduling problems may continue or worsen during new scheduling system integration. | Operational | High (3) | High(3) | 9 = High | Test the new scheduling process before full implementation. Monitor error during its implementation. Make sure the staff have clear guidance during the transition. | If there are significant scheduling errors during implementation, pause or limit the affected part of the workflow and use manual/previous process instead. Admin staff should manually review any affected appointments, correct errors, and contact any affected patients. Record the issues for the IT team. Re-implement the full workflow once the problem has been corrected and retested.
R-02 | Insuffient availability/poor allocation of resources (staff, rooms, and equipment) which continue to create bottlenecks contributing to patient delays. | Operational | High (3) | High(3) | 9 = High | Implement real-time resource tracking for both availability and status. Review resource usage data regularly and use the data when scheduling appointments and allocating resources. Test and validate resource visability with the operational staff before implementation. | If a crritical resouce shortage occurs, releavent staff should review the current resource availability and reprioritise the resources to the most critical areas/uses. Any affected appointments should be rescheduled and the patients should be contacted. Record the shortage so future resource decsisions are better.
R-03 | Patient waiting times do not improve if scheduling, check-in, and resource allocation improvements do not remove existing bottlenecks. | Operational | Medium (2) | High(3) | 9 = High | Establish a baseline for patient wait times, then monitor wait time changes after implementation. Review bottlenecks using data and take action where the 20% reduction target for wait time is not being achieved. | If the expected improvement is not being achieved, analyse workflow steps and departments to identify any remaining bottlenecks. Continue monitoring after correcting or making adjustments until performance hits the target.
R-04 | Poor quality interdepartmental handoffs, referrals, and transfer communincation may continue to cause delays, duplicated work or incomplete information during communication. | Operational | High (3) | High(3) | 9 = High | Implement standardised handoff/referral processes with required information fields, clear department ownership, and visible/live request status. Test and validate the workslow with operational staff and departments before implementation. Provide clear guidance during implementation | If hanoffs or referrals fail, the receiving department should contacte the sending apartment to get all the correct information and clarify ownership. Repeated failures should be logged and reviewed with the relevant departments and the any adjustements to the standarised process should be communicated and taught to relevant staff.
R-05 | System downtime may disrupt appointment booking, record retrival, communication, and other hospital operations. | Technical | High (3) | High(3) | 9 = High | Time system changes with the IT team. Fully test the system changes before implementing them. Minimise changes/updates during critical operating times. Keep the manual processes in place as a fallback if the automated systems fail. | If a system is unavailable, notify the IT team and activate the manual/alternatiive process for important activities. Staff should record important activities and information for later entry into the system once it is available again. Outstanding information should be inputted before resuming. Review cause and impact of the downtime.
R-06 | Patient or operational data could get exposed or compomised due to security vulnerabilities or changes to hospital systems. | Technical | Low (1) | High(3) | 3 = Medium | (Including this in mitigations because of the severity of occurance) Security audits and testing before implementation. Enforce encrpytion protocols. Identify and address legacy system vulnerabilities. Control access to sensitive data. Make sure the IT validate the security before integration. | If a breach occurs, notifiy the IT team. Isolate the breached system if possible. Identify the affected data and systems. Follow relevant security procedures. Conduct root cause analysis and implement emergency fixes. The systems should only go back to notmal after the issue had been fixed, contained, and validated.
R-07 | Legacy and new system integration may fail, or be delayed. | Technical | High (3) | High(3) | 9 = High | Complete early technical and integration analysis with the IT team. Test the interfaces and data flow before real hospital usage. Ensure there is reasonable time flexibility within the implementation plan to resolve issues fully. | If integration fails or implementation Is delayed, delay the failing systems rather than integrate while they are unstable or incompatible. Continue using existing systems where necessary. Wait for the IT team to investigate and resolve issues. Re-test the systems again before implementing. Revise the implementation schedule to reflect the delay.
R-08 | Incomplete or innacurate data might result in misleading dashboards, decisions, or assessment of project success | Technical | Medium (2) | Medium (2) | 4 = Medium
R-09 | Hospital staff might resist or fail to consistently use new workflows or systems due to lack of training, understanding, and involvement, or disagreement. | Stakeholder | High (3) | Medium (2) | 6 = High | Include staff using the new workflows/systems during testing and validation. Schedule specific training and clear guidance for all relevant staff. Communicate the purpose and banefits of the changes. Regularly collect staff feedback during the transition to issues can be addressed early. | If adoption remains low, identify the stakeholder groups where there are problems. Provide additional role-specific training and support. Gather feedback on why the resistance is occuring and use department champions to support colleagues and facilitate adoption. If necessary, reinforce existing procedures while problems are resolved.
R-10 | Patients may not all adopt the new online booking/check-in system because of usability or access difficulties. | Stakeholder | Medium (2) | Medium (2) | 4 = Medium
R-11 | Different stakeholder groups might have conflicting or misaligned expectations regarding the changes, leading to delays, dissatisfaction, or scope changes. | Stakeholder | Low (1) | Medium (2) | 2 = Low

## Risk Assessment Matrix
Risk Assessment Matrix
Likelihood
|  | High | Medium | Low
| High | R-01 R-02 R-04 R-05 R-07 | R-03 | R-06
Impact | Medium | R-09 | R-08 R-10 | R-11
| Low | - | - | -